## TimeCost Tracking
TIME COST SPREADSHEET
Anitha |  |  |  | Pavan
Date | Tasks | sub tasks | Duration[hr] | Date | Task | Sub Task | Duration[hr]
02.08.2019-15.08.2019 | Literature servey | Previous work has been done | 4 | 20.08.2019- 10.10.2019 | Literature servey |  | 10
02.08.2019-15.08.2019 | Literature servey | current research on the topic | 4
02.08.2019-15.08.2019 | Literature servey | Requirement gathering | 6
02.08.2019-15.08.2019 | Literature servey | Project plan | 6
02.08.2019-15.08.2019 | Literature servey | Project Meeting | 1
02.08.2019-15.08.2019 | Literature servey | Requirement finalising | 6
15.08.2019- 10.09.2019 | Class Identification | Data analysis | 4 | 20.08.2019- 10.10.2019 | Class indentification and understanding |  | 15
15.08.2019- 10.09.2019 | Class Identification | feature extraction | 5
15.08.2019- 10.09.2019 | Class Identification | Indentification of classes for segmentation | 6
15.08.2019- 10.09.2019 | Class Identification | Project meeting | 1
15.08.2019- 10.09.2019 | Ground truth | Mevislab set up | 2 | 20.08.2019- 10.10.2019 | Ground truth |  | 40
15.08.2019- 10.09.2019 | Ground truth | ground truth in mevislab | 15
10.08.2019- 20.09.2019 | Ground truth | research on efficient ways to derive ground truth | 6
10.08.2019- 20.09.2019 | Ground truth | research on efficient ways to derive ground truth(Deep labs) | 4
10.08.2019- 20.09.2019 | Ground truth | setting up phototshop | 2
10.08.2019- 20.09.2019 | Ground truth | work around in photoshop | 2
10.08.2019- 20.09.2019 | Ground truth | ground truth in photoshop | 16
10.08.2019- 20.09.2019 | Ground truth | project Meeting | 2
20.08.2019- 10.10.2019 | Architecture design | Research on CNN | 6 | 20.08.2019- 10.10.2019 | Architecture design | Research on CNN | 12
20.08.2019- 10.10.2019 | Architecture design | Research on unet | 3 | 20.08.2019- 10.10.2019 | Architecture design | Research on unet | 12
20.08.2019- 10.10.2019 | neural network development | Environment setup | 6 | 20.08.2019- 10.10.2019 | neural network development | Environment setup | 5
20.08.2019- 10.10.2019 | neural network development | Unet design | 8 | 20.08.2019- 10.10.2019 | neural network development | Unet design | 8
20.08.2019- 10.10.2019 | neural network development | Unet design | 8 | 20.08.2019- 10.10.2019 | neural network development | Unet design | 8
20.08.2019- 10.10.2019 | neural network development | Unet design | 4 | 20.08.2019- 10.10.2019 | neural network development | Unet design | 4
10.10.2019- 6.11.2019 | neural network development | Unet design | 3 | 10.10.2019- 6.11.2019 | neural network development | Unet design | 2
10.10.2019- 6.11.2019 | nueral network development | project Meeting | 2 | 10.10.2019- 6.11.2019 | nueral network development | project Meeting | 2
10.10.2019- 6.11.2019 | Training and testing | Training data for small data set | 8 | 10.10.2019- 6.11.2019 | Training and testing | Training data for small data set | 6
10.10.2019- 6.11.2019 | Training and testing | Testing the accuracy with small data set | 4 | 10.10.2019- 6.11.2019 | Training and testing | Testing the accuracy with small data set | 6
10.10.2019- 6.11.2019 | Training and testing | Training and testing | 5 | 10.10.2019- 6.11.2019 | Training and testing | Training and testing | 5
10.10.2019- 6.11.2019 | Ground truth | Ground truth | 10 | 10.10.2019- 6.11.2019 | Ground truth | Ground truth | 12
10.10.2019- 6.11.2019 | Ground truth | Ground truth | 10 | 10.10.2019- 6.11.2019 | Ground truth | Ground truth | 12
06-11-2019-28.11.2019 | Unet | Environment setup server | 6 | 06-11-2019-28.11.2019 | Unet | Environment setup server | 3
06-11-2019-28.11.2019 | unet | Generator design for batchwise approach | 6 | 06-11-2019-28.11.2019 | unet | Generator design for batchwise approach | 8
06-11-2019-28.11.2019 | ground truth | ground truth | 8 | 06-11-2019-28.11.2019 | ground truth | ground truth | 9
06-11-2019-28.11.2019 | ground truth | ground truth | 8 | 06-11-2019-28.11.2019 | ground truth | ground truth | 11
06-11-2019-28.11.2019 | ground truth | ground truth | 8 | 06-11-2019-28.11.2019 | ground truth | ground truth | 10
06-11-2019-28.11.2019 | Unet | Work on model(patch making) | 5 | 06-11-2019-28.11.2019 | Unet | Work on model(patch making) | 8
06-11-2019-28.11.2019 | Unet | Work on model | 6 | 06-11-2019-28.11.2019 | Unet | Work on model | 8
06-11-2019-28.11.2019 | Unet | Work on model | 6 | 06-11-2019-28.11.2019 | Unet | Work on model | 12
|  |  | 222 |  |  |  | 228

## Kosten
milestone | plan | actual | sum plan | sim actual | Planned Costs
Team | #REF! | #REF! | #REF! | #REF! | Actual Costs
Plan | #REF! | #REF! | #REF! | #REF! | Planned Cumulative Costs
Concept | #REF! | #REF! | #REF! | #REF! | Actual Cumulative Costs
Data | #REF! | #REF! | #REF! | #REF!
Model | #REF! | #REF! | #REF! | #REF!
Validation | #REF! | #REF! | #REF! | #REF!
Experiments | #REF! | #REF! | #REF! | #REF!
Report | #REF! | #REF! | #REF! | #REF!
Total | #REF! | #REF!

## Ist-Soll
| Woche | Soll | Ist
2019-04-01 | Start | 0 | 0 |  | Planned Progress
2019-04-08 | Miestone 1 | 6 | 8 |  | Actual Progress
2019-04-15 | Milestone 2 | 12 | 15
2019-04-22 | 4 | 15 | 19
2019-04-29 | Milestone 3 | 22 | 22
2019-05-06 | 6 | 36 | 35
2019-05-13 | Milestone 4 | 45 | 42
2019-05-20 | 8 | 58 | 60
2019-05-27 | Milestone 5 | 69 | 70
2019-06-03 | Milestone 6 | 80 | 77
2019-06-10 | 11 | 85 | 85
2019-06-17 | Milestone 7 | 90 | 88
2019-06-24 | Milestone 8 | 100 | 100
Kapitel #6
Feedbackgespräch #3
35 | 5.8333 | 5.8333
35 | 5.8333 | 11.6667 |  | Korrektur & Abgabe StA
60 | 10 | 21.6667 |  | Termin Verteidigung
140 | 23.3333 | 45
140 | 23.3333 | 68.3333 |  | Gliederung Präsentation
70 | 11.6667 | 80 |  | Feedbackgespräch #4
60 | 10 | 90 |  | Fertigstellung Präsentation
60 | 10 | 100 |  | Verteidigung

## Project Progress
Milestone | Responsibility | Start Date | End Date | Completion [%]
Team Formation | Dean | 2019-04-01 | 2019-04-07 | 100
Project Plan | Dean | 2019-04-08 | 2019-04-14 | 100
Conceptual Model | Julia | 2019-04-15 | 2019-04-28 | 100
Data Analysis | Tiru | 2019-04-29 | 2019-05-12 | 100
Simulation Program | Pavan | 2019-05-13 | 2019-05-26 | 25
Validation | Atrayee | 2019-05-27 | 2019-06-02
Simulation Experiments | Sinchana | 2019-06-03 | 2019-06-16
Final Report | All team members | 2019-06-17 | 2019-06-24

## Project Quality
Milestone | Actual Expense vs Planned Expense | Verification | Communication | Understandability of Results and Documentation | Modularity of simulation | Success of Validation | No. of Reworks
1 | #REF! | N/A | 1 - Good | 1 - Understandable | N/A | N/A | 0
2 | #REF! | N/A | 1 - Good | 1 - Understandable | N/A | N/A | 0
3 | #REF! | N/A | 1 - Good | 1 - Understandable | N/A | N/A | 0
4 | #REF!
5 | #REF!
6 | #REF!
7 | #REF!
8 | #REF!

## List
Team Communication | Verification / Success of Validation | Modularity of Simulation | Understandability | Effective Participation | Responsiblity | Creativity | Punctuality | Efficiency | Democratic | Guidance | Coordination
1 - Good | N/A | N/A | N/A | 1 - Active | 1 - Responsible | 1 - Creative | 1 - Punctual | 1 - Efficient | 1 - Democratic | 1 - Good Guidance | 1 - Good Coordinator
2 - Neutral | Success | 1 - Very Modular | 1 - Understandable | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
3 - Bad | Needs Rework | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
|  | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
|  | 4 | 4 | 5 - Not at all | 5 - Not at all | 5 - Not at all | 5 - Not at all | 5 - Not at all | 5 - Not at all | 5 - Not at all | 5 - Not at all
|  | 5 - Not at all | 5 - Not at all