## TimeCost Tracking
TIME COST SPREADSHEET - TEAM D
Milestone | Time IS | Time Planned (see project plan) | Costs IS | Costs Planned (see project plan) | Cumulated Costs IS | Cumulated Costs Planned
1 | 32.25 | 35 | 3225 | 3500 | 3225 | 3500
2 | 21.5 | 35 | 2150 | 3500 | 5375 | 7000
3 | 32.5 | 60 | 3250 | 6000 | 8625 | 13000
4 | 134.5 | 140 | 13450 | 14000 | 22075 | 27000
5 | 103.5 | 140 | 10350 | 14000 | 32425 | 41000
6 | 54 | 70 | 5400 | 7000 | 37825 | 48000
7 | 92.55 | 60 | 9255 | 9000 | 47080 | 57000
8 | 59 | 60 | 5900 | 6000 | 52980 | 63000
Sum | 529.8 | 620 | 52980 | 63000
Max | 620 |  | 63000
Atrayee |  |  |  | Dean |  |  |  | Julia |  |  |  | Pavan |  |  |  | Sinchana |  |  |  | Tiru
Date | Milestone | Task | Duration[hr] | Date | Milestone | Task | Duration[hr] | Date | Milestone | Task | Duration[hr] | Date | Milestone | Task | Duration[hr] | Date | Milestone | Task | Duration[hr] | Date | Milestone | Task | Duration[hr]
02.04.2019 | 1 | Team Meeting | 1 | 02.04.2019 | 1 | Team Meeting | 1 | 02.04.2019 | 1 | Team Meeting | 1 | 02.04.2019 | 1 | Team Meeting | 1 | 02.04.2019 | 1 | Team Meeting | 1 | 02.04.2019 | 1 | Team Meeting | 1
03.04.2019 | 1 | Site Visit | 1 | 03.04.2019 | 1 | Site Visit | 1 | 03.04.2019 | 1 | Site Visit | 1 | 07.04.2019 | 1 | Team Meeting | 2.5 | 03.04.2019 | 1 | Site Visit | 1 | 03.04.2019 | 1 | Site Visit | 1
05.04.2019 | 1 | Performance+QC Spreadsheet | 2.5 | 06.04.2019 | 1 | Prepare Presentation | 1 | 03.04.2019 | 1 | Create Time Cost Sheet | 0.5 | 08.04.2019 | 2 | Team Meeting | 1.5 | 07.04.2019 | 1 | Team Meeting | 2.5 | 07.04.2019 | 1 | Team Meeting | 2.5
07.04.2019 | 1 | Team Meeting | 2.5 | 07.04.2019 | 1 | Team Meeting | 2.5 | 05.04.2019 | 1 | Draw sketch from intersection | 1.25 | 13.04.2019 | 2 | Team Meeting | 1.5 | 08.04.2019 | 2 | Team Meeting | 1.5 | 08.04.2019 | 2 | Team Meeting | 1.5
08.04.2019 | 2 | Team Meeting | 1.5 | 08.04.2019 | 2 | Team Meeting | 1.5 | 07.04.2019 | 1 | Team Meeting | 2.5 | 15.04.2019 | 3 | Team Meeting | 1.5 | 03.04.2019 | 4 | Site Visit | 0.75 | 03.04.2019 | 4 | Site Visit | 0.75
03.04.2019 | 4 | Site Visit | 0.75 | 03.04.2019 | 4 | Site Visit | 0.75 | 07.04.2019 | 1 | Add overview about KPIs | 1 | 22.04.2019 | 5 | Started Building Base model in Anylogic | 3 | 13.04.2019 | 2 | Team Meeting | 1.5 | 13.04.2019 | 2 | Team Meeting | 1.5
13.04.2019 | 2 | Team Meeting | 1.5 | 13.04.2019 | 2 | Team Meeting | 1.5 | 08.04.2019 | 2 | Team Meeting | 1.5 | 22.04.2019 | 3 | Team Meeting | 1 | 15.04.2019 | 3 | Team Meeting | 1.5 | 15.04.2019 | 3 | Team Meeting | 1.5
15.04.2019 | 3 | Team Meeting | 1.5 | 13.04.2019 | 2 | Prepare Presentation | 3 | 03.04.2019 | 4 | Site Visit | 0.75 | 22.04.2019 | 4 | Team Meeting | 1 | 22.04.2019 | 3 | Team Meeting | 1 | 22.04.2019 | 3 | Team Meeting | 1
13.04.2019 | 2 | Review Presentation | 1.5 | 15.04.2019 | 3 | Team Meeting | 1.5 | 17.04.2019 | 3 | Create Conceptual Model | 4 | 23.04.2019 | 3 | Slack Messages | 0.25 | 22.04.2019 | 4 | Team Meeting | 1 | 22.04.2019 | 4 | Team Meeting | 1
22.04.2019 | 3 | Team Meeting | 1 | 22.04.2019 | 3 | Team Meeting | 1 | 18.04.2019 | 3 | Create Conceptual Model | 1 | 23.04.2019 | 4 | Data collection requirement review | 0.5 | 25.04.2019 | 4 | Team Meeting | 1.5 | 28.04.2019 | 4 | Template | 1
22.04.2019 | 4 | Team Meeting | 1 | 22.04.2019 | 4 | Team Meeting | 1 | 20.04.2019 | 3 | Create Conceptual Model | 3 | 25.04.2019 | 4 | Team Meeting | 1.5 | 26.04.2019 | 7 | Software Videos | 1.5 | 29.04.2019 | 4 | Team Meeting | 1
23.04.2019 | 3 | Slack Messages | 0.25 | 23.04.2019 | 3 | Slack Messages | 0.25 | 15.04.2019 | 3 | Team Meeting | 1.5 | 25.04.2019 | 5 | SoftwareModel | 4 | 29.04.2019 | 4 | Team Meeting | 1 | 30.04.2019 | 4 | Data Collection | 1.5
25.04.2019 | 4 | Team Meeting | 1.5 | 25.04.2019 | 4 | Team Meeting | 1.5 | 14.04.2019 | 3 | Prepare Homework | 1.5 | 25.04.2019 | 5 | SoftwareModel | 2 | 30.04.2019 | 4 | Data Collection | 1.5 | 03.05.2019 | 4 | Data Collection | 1.5
29.04.2019 | 4 | Team Meeting | 1 | 25.04.2019 | 2 | Evaluation Template | 0.5 | 13.04.2019 | 3 | Go through meeting minutes | 0.5 | 26.04.2019 | 5 | SoftwareModel | 4 | 30.04.2019 | 4 | Slack Messages & Discussions | 0.25 | 04.05.2019 | 4 | Converting Data | 2
30.04.2019 | 4 | Data Collection | 1.5 | 25.04.2019 | 4 | Data Collection Template | 0.25 | 22.04.2019 | 3 | Team Meeting | 1 | 29.04.2019 | 4 | Team Meeting | 1 | 03.05.2019 | 4 | Data Collection | 1.5 | 04.05.2019 | 4 | Distributions | 1
30.04.2019 | 4 | Slack Messages & Discussions | 0.25 | 28.04.2019 | 3 | Presentation | 1.5 | 22.04.2019 | 4 | Team Meeting | 1 | 30.04.2019 | 4 | Data Collection | 1.5 | 06.05.2019 | 4 | Data Collection | 1 | 06.05.2019 | 4 | Data Collection | 1
03.05.2019 | 4 | Data Collection | 1.5 | 29.04.2019 | 4 | Team Meeting | 1 | 23.04.2019 | 3 | Slack Messages | 0.25 | 30.04.2019 | 4 | Slack Messages & Discussions | 0.25 | 06.05.2019 | 4 | Team Meeting | 1 | 06.05.2019 | 4 | Team Meeting | 1
06.05.2019 | 4 | Data Collection | 1 | 30.04.2019 | 4 | Data Collection | 1.5 | 23.04.2019 | 3 | Go through petri net again | 2 | 03.05.2019 | 4 | Data Collection | 1.5 | 07.05.2019 | 4 | Data Collection | 1 | 07.05.2019 | 4 | Data Collection | 1
06.05.2019 | 4 | Team Meeting | 1 | 30.04.2019 | 4 | Slack Messages & Discussions | 0.25 | 24.04.2019 | 3 | Prepare presentation | 3 | 06.05.2019 | 4 | Data Collection | 1 | 10.05.2019 | 4 | Data processing | 5 | 07.05.2019 | 4 | Converting Data | 1
07.05.2019 | 4 | Data Collection | 1 | 03.05.2019 | 4 | Data Collection | 1.5 | 25.04.2019 | 4 | Team Meeting | 1.5 | 06.05.2019 | 4 | Team Meeting | 1 | 15.05.2019 | 7 | Experiment 1 | 0.3 | 08.05.2019 | 4 | Distributions | 1
10.05.2019 | 4 | Data processing | 5 | 06.05.2019 | 4 | Data Collection | 1 | 25.04.2019 | 4 | Data Collection Template | 0.25 | 07.05.2019 | 4 | Data Collection | 1 | 16.05.2019 | 7 | Experiment 1 | 0.45 | 08.05.2019 | 4 | Chi-Square | 1
13.05.2019 | 4 | Team Meeting | 1.5 | 06.05.2019 | 4 | Team Meeting | 1 | 29.04.2019 | 4 | Team Meeting | 1 | 09.05.2019 | 5 | Pedestrains Model | 7 | 13.05.2019 | 4 | Team Meeting | 1.5 | 08.05.2020 | 4 | Q-Q Plot | 1
17.05.2019 | 4 | Data Collection | 1.5 | 07.05.2019 | 4 | Data Collection | 1 | 30.04.2019 | 4 | Data Collection | 1.5 | 09.05.2019 | 5 | Tram model | 2 | 16.05.2019 | 4 | Team Meeting | 1.5 | 10.05.2019 | 4 | Data processing | 5
24.05.2019 | 6 | Queue Length distribution estimation | 4 | 16.05.2019 | 4 | Team Meeting | 1.5 | 30.04.2019 | 4 | Slack Messages & Discussions | 0.25 | 10.05.2019 | 4 | Data processing | 5 | 20.05.2019 | 4 | Team Meeting | 1.5 | 11.05.2019 | 4 | Data Processing | 3
26.05.2019 | 6 | Initial study for parameter estimation | 2 | 20.05.2019 | 4 | Team Meeting | 2 | 03.05.2019 | 4 | Data Collection | 1.5 | 12.05.2019 | 5 | modelling | 5 | 24.05.2019 | 5 | Simulation work | 4 | 12.05.2019 | 4 | Prepare Presentation | 4
16.05.2019 | 4 | Team Meeting | 1.5 | 20.05.2019 | 5 | Team Meeting | 1 | 06.05.2019 | 4 | Data Collection | 1 | 13.05.2019 | 5 | Reasearch for model | 5 | 27.05.2019 | 6 | Team Meeting | 1.5 | 12.05.2019 | 4 | Review & Chnges | 1
20.05.2019 | 4 | Team Meeting | 2 | 24.05.2019 | 5 | Simulation work | 4 | 06.05.2019 | 4 | Team Meeting | 1 | 15.05.2019 | 5 | Implementation | 4 | 01.06.2019 | 6 | Validation | 2 | 13.05.2019 | 4 | Team Meeting | 1.5
20.05.2019 | 5 | Team Meeting | 1 | 27.05.2019 | 6 | Team Meeting | 1.5 | 07.05.2019 | 4 | Data Collection | 1 | 17.05.2019 | 5 | modelling | 7.5 | 02.06.2019 | 7 | Experiments Info Gathering | 0.3 | 17.05.2019 | 4 | Data Collection | 1.5
24.05.2019 | 5 | Simulation work | 4 | 29.05.2019 | 6 | Validation work | 3 | 10.05.2019 | 4 | Data processing | 5 | 17.05.2019 | 5 | modelling | 3.5 | 04.06.2019 | 7 | Optimization of traffic lights(started) | 0 | 16.05.2019 | 4 | Team Meeting | 1.5
27.05.2019 | 6 | Team Meeting | 1.5 | 31.05.2019 | 6 | Validation work | 3 | 18.05.2019 | 4 | Data processing | 3 | 13.05.2019 | 4 | Team Meeting | 1.5 | 05.06.2019 | 7 | Random seed generation and optimization experiment | 1 | 24.05.2019 | 5 | Simulation work | 4
29.05.2019 | 6 | Verify Distributions | 1 | 17.06.3019 | 8 | Team Meeting | 1.5 | 18.05.2019 | 4 | Messages | 0.5 | 18.05.2019 | 5 | modelling | 2.5 | 12.06.2019 | 7 | Run experiments | 8 | 27.05.2019 | 6 | Team Meeting | 1.5
31.05.2019 | 6 | Create Queue Length Experiment | 2 | 21.06.2019 | 8 | Meeting | 1.5 | 13.05.2019 | 4 | Team Meeting | 1.5 | 19.05.2019 | 5 | Bus stop modelling | 5 | 11.06.2019 | 7 | Prepare experiments | 4 | 17.06.3019 | 8 | Team Meeting | 1.5
30.05.2019 | 6 | Work on model | 2 | 20.06.2019 | 8 | Documentation | 3 | 17.05.2019 | 4 | Data Collection | 1.5 | 20.05.2019 | 5 | putting it all together | 7 | 07.06.2019 | 7 | Prepare experiments | 6 | 21.06.2019 | 8 | Meeting | 1.5
01.06.2019 | 6 | Work on model | 2 | 22.06.2019 | 8 | Documentation | 2 | 16.05.2019 | 4 | Team Meeting | 1.5 | 21.05.2019 | 5 | verification | 2 | 10.06.2019 | 7 | Prepare experiments | 6 | 23.06.2019 | 8 | Messages | 1
02.06.2019 | 6 | Create Throughput Experiment | 2 | 23.06.2019 | 8 | Documentation | 5 | 20.05.2019 | 6 | Team Meeting | 1.5 | 22.05.2019 | 5 | updating model after verifiaction | 8 | 06.06.2019 | 7 | Prepare experiments | 5
31.05.2019 | 6 | Data Processing | 1 | 23.06.2019 | 8 | Messages | 1 | 27.05.2019 | 6 | Team Meeting | 1.5 | 23.05.2019 | 5 | Presentation preparation | 3 | 13.06.2019 | 7 | Experiment 1 | 2
01.06.2019 | 6 | Presentation draft | 1 |  |  |  |  | 30.05.2019 | 6 | Work on validation | 2 | 16.05.2019 | 5 | alternate ped model | 6 | 14.06.2019 | 7 | Experiment 2 | 6
31.05.2019 | 6 | Verify Distributions | 2 |  |  |  |  | 31.05.2019 | 6 | Work on distributions | 2.5 | 16.05.2019 | 4 | Team Meeting | 1.5 | 15.06.2019 | 7 | Experiment 3 | 7
02.06.2019 | 6 | Final presentation | 2 |  |  |  |  | 30.05.2019 | 6 | Work on model | 2 | 20.05.2019 | 4 | Team Meeting | 2 | 16.06.2019 | 7 | Experiment 4 | 4
10.06.2019 | 7 | Experiments | 2 |  |  |  |  | 01.06.2019 | 6 | Work on model | 4.5 | 20.05.2019 | 5 | Team Meeting | 1 | 15.04.2016 | 7 | Presentation | 4
12.06.2019 | 7 | Experiments | 3 |  |  |  |  | 31.05.2019 | 6 | Verify Distributions | 3 | 24.05.2019 | 5 | Simulation work | 4 | 17.06.3019 | 8 | Team Meeting | 1.5
14.06.2019 | 7 | Experiments | 3 |  |  |  |  | 02.06.2019 | 6 | Go through presentation | 0.5 | 27.05.2019 | 6 | Team Meeting | 1.5 | 21.06.2019 | 8 | Meeting | 1.5
15.06.2019 | 7 | Experiments | 1 |  |  |  |  | 12.06.2019 | 7 | Run experiments | 9 | 10.06.2019 | 7 | Experiments | 2 | 23.06.2019 | 8 | Messages | 1
17.06.3019 | 8 | Team Meeting | 1.5 |  |  |  |  | 11.06.2019 | 7 | Prepare experiments | 3 | 12.06.2019 | 7 | Experiments | 3
21.06.2019 | 8 | Meeting | 1.5 |  |  |  |  | 10.06.2019 | 7 | Prepare experiments | 4 | 14/06.2019 | 7 | Experiments | 3
23.06.2019 | 8 | Messages | 1 |  |  |  |  | 7.06.2019 | 7 | Prepare experiments | 3 | 15.06.2019 | 7 | Experiments | 1
[8 empty] | 17.06.3019 | 8 | Team Meeting | 1.5 | 17.06.3019 | 8 | Team Meeting | 1.5
[8 empty] | 10.06.2019 | 8 | Documentation | 8 | 21.06.2019 | 8 | Meeting | 1.5
[8 empty] | 21.06.2019 | 8 | Meeting | 1.5 | 23.06.2019 | 8 | Messages | 1
[8 empty] | 22.06.2019 | 8 | Final Presentation | 6
[8 empty] | 20.06.2019 | 8 | Final Presentation | 3
[8 empty] | 15.06.2019 | 8 | Documentation | 2
[8 empty] | 23.06.2019 | 8 | Final Presentation | 6
[8 empty] | 23.06.2019 | 8 | Messages | 1

## Kosten
milestone | plan | actual | sum plan | sim actual | Planned Costs
Team | 35 | 32.25 | 35 | 32.25 | Actual Costs
Plan | 35 | 21.5 | 70 | 53.75 | Planned Cumulative Costs
Concept | 60 | 32.5 | 130 | 86.25 | Actual Cumulative Costs
Data | 140 | 134.5 | 270 | 220.75
Model | 140 | 103.5 | 410 | 324.25
Validation | 70 | 54 | 480 | 378.25
Experiments | 90 | 92.55 | 570 | 470.8
Report | 60 | 59 | 630 | 529.8
Total | 630 | 529.8

## Ist-Soll
| Woche | Soll | Ist
2019-04-01 | Start | 0 | 0 |  | Planned Progress
2019-04-08 | Miestone 1 | 6 | 8 |  | Actual Progress
2019-04-15 | Milestone 2 | 12 | 15
2019-04-22 | 4 | 15 | 19
2019-04-29 | Milestone 3 | 22 | 22
2019-05-06 | 6 | 36 | 35
2019-05-13 | Milestone 4 | 45 | 42
2019-05-20 | 8 | 58 | 60
2019-05-27 | Milestone 5 | 69 | 70
2019-06-03 | Milestone 6 | 80 | 77
2019-06-10 | 11 | 85 | 85
2019-06-17 | Milestone 7 | 90 | 88
2019-06-24 | Milestone 8 | 100 | 100
Kapitel #6
Feedbackgespräch #3
35 | 5.8333 | 5.8333
35 | 5.8333 | 11.6667 |  | Korrektur & Abgabe StA
60 | 10 | 21.6667 |  | Termin Verteidigung
140 | 23.3333 | 45
140 | 23.3333 | 68.3333 |  | Gliederung Präsentation
70 | 11.6667 | 80 |  | Feedbackgespräch #4
60 | 10 | 90 |  | Fertigstellung Präsentation
60 | 10 | 100 |  | Verteidigung

## Project Progress
Milestone | Responsibility | Start Date | End Date | Completion [%]
Team Formation | Dean | 2019-04-01 | 2019-04-07 | 100
Project Plan | Dean | 2019-04-08 | 2019-04-14 | 100
Conceptual Model | Julia | 2019-04-15 | 2019-04-28 | 100
Data Analysis | Tiru | 2019-04-29 | 2019-05-12 | 100
Simulation Program | Pavan | 2019-05-13 | 2019-05-26 | 25
Validation | Atrayee | 2019-05-27 | 2019-06-02
Simulation Experiments | Sinchana | 2019-06-03 | 2019-06-16
Final Report | All team members | 2019-06-17 | 2019-06-24

## Project Quality
Milestone | Actual Expense vs Planned Expense | Verification | Communication | Understandability of Results and Documentation | Modularity of simulation | Success of Validation | No. of Reworks
1 | 0.92 | N/A | 1 - Good | 1 - Understandable | N/A | N/A | 0
2 | 0.61 | N/A | 1 - Good | 1 - Understandable | N/A | N/A | 0
3 | 0.54 | N/A | 1 - Good | 1 - Understandable | N/A | N/A | 0
4 | 0.96
5 | 0.74
6 | 0.77
7 | 1.03
8 | 0.98

## Individual - Total
|  | Individual | [5 empty] | Role Based
Weeks | Member | Effective Participation | Responsiblity | Creativity | Punctuality | Efficiency | Democratic | Guidance | Coordination
1 - 2 | Atrayee
| Dean | 1.2
Julia
Pavan
Sinchana
Tirupathi
3 - 4 | Atrayee
Dean
Julia
Pavan
Sinchana
Tirupathi
5 - 6 | Atrayee
Dean
Julia
Pavan
Sinchana
Tirupathi
7 - 8 | Atrayee
Dean
Julia
Pavan
Sinchana
Tirupathi
9 - 10 | Atrayee
Dean
Julia
Pavan
Sinchana
Tirupathi
11 - 12 | Atrayee
Dean
Julia
Pavan
Sinchana
Tirupathi

## Atrayee
|  | Individual | [5 empty] | Role Based
Weeks | Member | Effective Participation | Responsiblity | Creativity | Punctuality | Efficiency | Democratic | Guidance | Coordination
1 - 2 | Atrayee | 2 | 2 | 2 | 2 | 2 | 2
| Dean | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Julia | 1 | 1 | 1 | 1 | 1 | 1
| Pavan | 1 | 1 | 1 | 1 | 1 | 1
| Sinchana | 1 | 1 | 1 | 1 | 1 | 1
| Tirupathi | 3 | 3 | 3 | 2 | 3 | 3
3 - 4 | Atrayee
| Dean | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Julia | 1 | 1 | 1 | 1 | 1 | 1
| Pavan | 1 | 1 | 1 | 1 | 1 | 1
| Sinchana | 1 | 1 | 1 | 1 | 1 | 1
| Tirupathi | 3 | 3 | 3 | 3 | 4 | 3
5 - 6 | Atrayee
Dean
Julia
Pavan
Sinchana
Tirupathi
7 - 8 | Atrayee
Dean
Julia
Pavan
Sinchana
Tirupathi
9 - 10 | Atrayee
Dean
Julia
Pavan
Sinchana
Tirupathi
11 - 12 | Atrayee
Dean
Julia
Pavan
Sinchana
Tirupathi

## Dean
|  | Individual | [5 empty] | Role Based
Weeks | Member | Effective Participation | Responsiblity | Creativity | Punctuality | Efficiency | Democratic | Guidance | Coordination
1 - 2 | Atrayee | 1 - Active | 1 - Responsible | 1 - Creative | 1 - Punctual | 1 - Efficient | 1 - Democratic
| Dean | 1 - Active | 1 - Responsible | 2 | 1 - Punctual | 3 | 1 - Democratic | 2 | 2
| Julia | 1 - Active | 1 - Responsible | 1 - Creative | 1 - Punctual | 1 - Efficient | 3
| Pavan | 1 - Active | 1 - Responsible | 1 - Creative | 1 - Punctual | 1 - Efficient | 1 - Democratic
| Sinchana | 1 - Active | 1 - Responsible | 1 - Creative | 1 - Punctual | 1 - Efficient | 1 - Democratic
| Tirupathi | 2 | 3 | 3 | 1 - Punctual | 3 | 1 - Democratic
3 - 4 | Atrayee | 1 - Active | 1 - Responsible | 1 - Creative | 1 - Punctual | 1 - Efficient | 1 - Democratic
| Dean | 1 - Active | 1 - Responsible | 2 | 1 - Punctual | 2 | 1 - Democratic | 2 | 2
| Julia | 1 - Active | 1 - Responsible | 1 - Creative | 1 - Punctual | 1 - Efficient | 3
| Pavan | 1 - Active | 1 - Responsible | 1 - Creative | 1 - Punctual | 1 - Efficient | 1 - Democratic
| Sinchana | 1 - Active | 1 - Responsible | 1 - Creative | 1 - Punctual | 1 - Efficient | 1 - Democratic
| Tirupathi | 4 | 3 | 3 | 2 | 4 | 1 - Democratic
5 - 6 | Atrayee
Dean
Julia
Pavan
Sinchana
Tirupathi
7 - 8 | Atrayee
Dean
Julia
Pavan
Sinchana
Tirupathi
9 - 10 | Atrayee
Dean
Julia
Pavan
Sinchana
Tirupathi
11 - 12 | Atrayee
Dean
Julia
Pavan
Sinchana
Tirupathi

## Julia
|  | Individual | [5 empty] | Role Based
Weeks | Member | Effective Participation | Responsiblity | Creativity | Punctuality | Efficiency | Democratic | Guidance | Coordination
1 - 2 | Atrayee | 1 - Active | 1 - Responsible | 1 - Creative | 1 - Punctual | 3 | 1 - Democratic
| Dean | 1 - Active | 1 - Responsible | 1 - Creative | 1 - Punctual | 3 | 1 - Democratic | 2 | 3
| Julia | 1 - Active | 1 - Responsible | 1 - Creative | 1 - Punctual | 3 | 1 - Democratic
| Pavan | 1 - Active | 1 - Responsible | 1 - Creative | 1 - Punctual | 3 | 1 - Democratic
| Sinchana | 1 - Active | 1 - Responsible | 1 - Creative | 1 - Punctual | 3 | 1 - Democratic
| Tirupathi | 1 - Active | 2 | 3 | 1 - Punctual | 3 | 1 - Democratic
3 - 4 | Atrayee | 1 - Active | 1 - Responsible | 1 - Creative | 1 - Punctual | 2 | 1 - Democratic
| Dean | 1 - Active | 1 - Responsible | 1 - Creative | 1 - Punctual | 2 | 1 - Democratic | 2 | 1 - Good Coordinator
| Julia | 1 - Active | 1 - Responsible | 1 - Creative | 1 - Punctual | 2 | 1 - Democratic
| Pavan | 1 - Active | 1 - Responsible | 1 - Creative | 1 - Punctual | 2 | 1 - Democratic
| Sinchana | 1 - Active | 1 - Responsible | 1 - Creative | 1 - Punctual | 2 | 1 - Democratic
| Tirupathi | 3 | 3 | 3 | 4 | 2 | 1 - Democratic
5 - 6 | Atrayee
Dean
Julia
Pavan
Sinchana
Tirupathi
7 - 8 | Atrayee
Dean
Julia
Pavan
Sinchana
Tirupathi
9 - 10 | Atrayee
Dean
Julia
Pavan
Sinchana
Tirupathi
11 - 12 | Atrayee
Dean
Julia
Pavan
Sinchana
Tirupathi

## Pavan
|  | Individual | [5 empty] | Role Based
Weeks | Member | Effective Participation | Responsiblity | Creativity | Punctuality | Efficiency | Democratic | Guidance | Coordination
1 - 2 | Atrayee | 1 - Active | 1 - Responsible | 1 - Creative | 1 - Punctual | 1 - Efficient | 1 - Democratic
| Dean | 1 - Active | 1 - Responsible | 1 - Creative | 1 - Punctual | 1 - Efficient | 1 - Democratic | 1 - Good Guidance | 1 - Good Coordinator
| Julia | 1 - Active | 1 - Responsible | 1 - Creative | 1 - Punctual | 1 - Efficient | 1 - Democratic
| Pavan | 1 - Active | 1 - Responsible | 1 - Creative | 1 - Punctual | 1 - Efficient | 1 - Democratic
| Sinchana | 1 - Active | 1 - Responsible | 1 - Creative | 1 - Punctual | 1 - Efficient | 1 - Democratic
| Tirupathi | 1 - Active | 2 | 2 | 1 - Punctual | 2 | 1 - Democratic
3 - 4 | Atrayee | 1 - Active | 1 - Responsible | 1 - Creative | 1 - Punctual | 1 - Efficient | 1 - Democratic
| Dean | 1 - Active | 1 - Responsible | 1 - Creative | 1 - Punctual | 1 - Efficient | 1 - Democratic | 1 - Good Guidance | 1 - Good Coordinator
| Julia | 1 - Active | 1 - Responsible | 1 - Creative | 1 - Punctual | 1 - Efficient | 1 - Democratic
| Pavan | 1 - Active | 1 - Responsible | 1 - Creative | 1 - Punctual | 1 - Efficient | 1 - Democratic
| Sinchana | 1 - Active | 1 - Responsible | 1 - Creative | 1 - Punctual | 1 - Efficient | 1 - Democratic
| Tirupathi | 2 | 1 - Responsible | 1 - Creative | 1 - Punctual | 2 | 1 - Democratic
5 - 6 | Atrayee
Dean
Julia
Pavan
Sinchana
Tirupathi
7 - 8 | Atrayee
Dean
Julia
Pavan
Sinchana
Tirupathi
9 - 10 | Atrayee
Dean
Julia
Pavan
Sinchana
Tirupathi
11 - 12 | Atrayee
Dean
Julia
Pavan
Sinchana
Tirupathi

## Sinchana
|  | Individual | [5 empty] | Role Based
Weeks | Member | Effective Participation | Responsiblity | Creativity | Punctuality | Efficiency | Democratic | Guidance | Coordination
1 - 2 | Atrayee | 1 - Active | 1 - Responsible | 1 - Creative | 1 - Punctual | 1 - Efficient | 1 - Democratic
| Dean | 1 - Active | 1 - Responsible | 1 - Creative | 1 - Punctual | 1 - Efficient | 1 - Democratic | 1 - Good Guidance | 1 - Good Coordinator
| Julia | 1 - Active | 1 - Responsible | 1 - Creative | 1 - Punctual | 1 - Efficient | 1 - Democratic
| Pavan | 1 - Active | 1 - Responsible | 1 - Creative | 1 - Punctual | 1 - Efficient | 1 - Democratic
| Sinchana | 2 | 1 - Responsible | 2 | 1 - Punctual | 2 | 1 - Democratic
| Tirupathi | 2 | 2 | 3 | 1 - Punctual | 3 | 2
3 - 4 | Atrayee | 1 - Active | 1 - Responsible | 1 - Creative | 1 - Punctual | 1 - Efficient | 1 - Democratic
| Dean | 1 - Active | 1 - Responsible | 1 - Creative | 1 - Punctual | 1 - Efficient | 1 - Democratic | 1 - Good Guidance | 1 - Good Coordinator
| Julia | 1 - Active | 1 - Responsible | 1 - Creative | 1 - Punctual | 1 - Efficient | 1 - Democratic
| Pavan | 1 - Active | 1 - Responsible | 1 - Creative | 1 - Punctual | 1 - Efficient | 1 - Democratic
| Sinchana | 2 | 2 | 2 | 1 - Punctual | 2 | 1 - Democratic
| Tirupathi | 3 | 3 | 2 | 2 | 3 | 2
5 - 6 | Atrayee
Dean
Julia
Pavan
Sinchana
Tirupathi
7 - 8 | Atrayee
Dean
Julia
Pavan
Sinchana
Tirupathi
9 - 10 | Atrayee
Dean
Julia
Pavan
Sinchana
Tirupathi
11 - 12 | Atrayee
Dean
Julia
Pavan
Sinchana
Tirupathi

## Tiru
|  | Individual | [5 empty] | Role Based
Weeks | Member | Effective Participation | Responsiblity | Creativity | Punctuality | Efficiency | Democratic | Guidance | Coordination
1 - 2 | Atrayee
| Dean | 2
Julia
Pavan
Sinchana
Tirupathi
3 - 4 | Atrayee
Dean
Julia
Pavan
Sinchana
Tirupathi
5 - 6 | Atrayee
Dean
Julia
Pavan
Sinchana
Tirupathi
7 - 8 | Atrayee
Dean
Julia
Pavan
Sinchana
Tirupathi
9 - 10 | Atrayee
Dean
Julia
Pavan
Sinchana
Tirupathi
11 - 12 | Atrayee
Dean
Julia
Pavan
Sinchana
Tirupathi

## Julia´s ideas about KPIs
Explanations: |  | GREY = Peer reviews -> Template and frequency (every 2 weeks/after each milestone/...) for peer reviews needed! |  |  |  | Applies always -> measured for each milestone | Applies only for specific milestones
Individual Performance | [5 empty] | Project Quality
Measured for all team members separately (-> template in section "Individual") |  |  | Measured only for the role responsible
Category | Criterion | Methode of measurement | Role | Criterion | Method of measurement | Criterion | Method of Measure
Soft Skills | Active participation / Takes initiative when appropriate / Contributes to the project | Peer review every 2(?) weeks / after each milestone (?) Scale: 1-5, 1:actively participating, 5: not at all participating | Team Leader | Guides through the meetings with a "red thread" | Peer review every 2(?) weeks / after each milestone (?) Scale: 1-5, 1: good guidance, 5: very bad guidance | Cost Tracking | Equation: Value = Actual Expense / Planned Expense If Value <= 1, this KPI is "green" in the presentation, otherwise it is red
| Responsibility | Peer review every 2(?) weeks / after each milestone (?) Scale:0-1, 1:responsible, 5:irresponsible |  | Ensures that all milestones are reached in time according to project plan | Alle milestones reached in time? -> Yes/No indicate green/red | Number of reworks after task was already reviewed and "Done" in Trello | Count number of reworks One Rework per 2 milestones is "free", so if we have one rework after milestone 2 this field will indicate "green" in the presentation. If we have 3 reworks after 2 milestones it will appear "red"
| Creativity | Peer review every 2(?) weeks / after each milestone (?) Scale: 1-5, 1:very creative, 5:not at all creative |  | Coordinates within the team in case of long discussions or misunderstandings | Peer review every 2(?) weeks / after each milestone (?) Scale: 1-5, 1: good coordination, 5: very bad coordination | Modularity of simulation | Subjective estimation, like: Is the simulation model structured they way it was defined beforehand, e.g. use functions for code that is called multiple times -> Will be assessed once a draft of the simulation model is available (1-5, 1: very modular, 5: not at all modular)
| Democratic / Is open for different proposals and accepts other´s opinions and also is willing to find compromises | Peer review every 2(?) weeks / after each milestone (?) Scale: 1-5, 1:very democratic, 5:not at all democratic | all other roles do NOT have such kind of individual criteria according to their responsibility |  |  | Compactness/accuracy of the single results per milestone and understandability of documentation | Did the responsible person for a topic provide an adequate documentation of his/her thoughts, so that everyone can understand BEFORE the team meeting how the results were achieved and can prepare questions? Is the documentation well understandable? Will be assessed after each meeting for the respective person that prepared results fpr the team meeting (1-5, 1: well understandable and documented, 5: not at all understandable)
| Punctuality | Count how often sb is not in time for a meeting How often does somebody not handing in something/finishing the task by the time and date specified? Everyone has 1 time "free" so that this KPI in the presentation still shows green |  |  |  | Success of validation | Is the validation at the very end of the project successful? -> Yes/No indicate green or red -> Only applies after validation was done
| Efficiency in meetings, communication and work | Peer review every 2(?) weeks / after each milestone (?) Scale: 1-5, 1:very efficient, 5:not at all efficient

## List
Team Communication | Verification / Success of Validation | Modularity of Simulation | Understandability | Effective Participation | Responsiblity | Creativity | Punctuality | Efficiency | Democratic | Guidance | Coordination
1 - Good | N/A | N/A | N/A | 1 - Active | 1 - Responsible | 1 - Creative | 1 - Punctual | 1 - Efficient | 1 - Democratic | 1 - Good Guidance | 1 - Good Coordinator
2 - Neutral | Success | 1 - Very Modular | 1 - Understandable | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
3 - Bad | Needs Rework | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
|  | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
|  | 4 | 4 | 5 - Not at all | 5 - Not at all | 5 - Not at all | 5 - Not at all | 5 - Not at all | 5 - Not at all | 5 - Not at all | 5 - Not at all
|  | 5 - Not at all | 5 - Not at all